## BACKEND TEST EXECUTE
Backend Test Execute and Reporting
Objective: Ensure that the System Under Test (SUT) meets all defined functional, security, performance, and usability requirements. Ensure that the system delivers an optimal, error-free experience for both users and stakeholders.
Description: Implement a comprehensive set of tests designed to validate system functionality, integrity, and performance. This includes verifying component interaction, identifying and documenting defects, and confirming that any changes or upgrades do not affect the stability of the existing system.
Invitation to the workplace in Postman: https://app.getpostman.com/join-team?invite_code=f4ec862b82ba348b9b64c289b7e69a8510d650c5e7e15e6c3e44f9ecd8e3245f&target_code=5989b00b57b30b59d7ab372eebc98c39
Fecha: 19/04/2025
Login
Description | Preconditions | Action | Data | Expected Results | Results Obtained | Observaciones | Evidence | PASS | Bug
TC1: Validate successful login by entering Username and Password correctly. | * The user must be previously registered. * The user must have a username and password." | * Log in using the POST method with the URL {{base_url}}/api/User/login | {"username": "testeruser", "password": "password" } | * It should show status 200 OK. | * Status 200 was obtained. |  |  | PASSED
TC2: Validate that cannot log in by leaving the Username field empty and the Password correct. |  | * Log in using the POST method with the URL {{base_url}}/api/User/login | { "username": null, "password": "password" } | * It should show status 400 Bad Request | * 400 Bad Requests were received |  |  | PASSED
TC3: Validate Unable to log in using correct Username and empty Password. |  | * Log in using the POST method with the URL {{base_url}}/api/User/login | { "username": "testuser", "password": null } | * It should show status 400 Bad Request | * 400 Bad Requests were received |  |  | PASSED
TC4: Validate Unable to log in leaving all fields empty. |  | * Log in using the POST method with the URL {{base_url}}/api/User/login | { "username": null, "password": null } | * It should show status 400 Bad Request | * 400 Bad Requests were received |  |  | PASSED
TC5: Validate Unable to log in using correct Username and incorrect Password. |  | * Log in using the POST method with the URL {{base_url}}/api/User/login | { "username": "username", "password": "Carmen" } | * It should show status 401 Unauthorized | * 401 Unauthorized was obtained |  |  | PASSED
TC6: Validate Unable to log in using incorrect username and correct password. |  | * Log in using the POST method with the URL {{base_url}}/api/User/login | { "username": "Daniela", "password": "password" } | * It should show status 401 Unauthorized | * 401 Unauthorized was obtained |  |  | PASSED
TC7: Validate Unable to log in when using Incorrect data. |  | * Log in using the POST method with the URL {{base_url}}/api/User/login | { "username": "Daniela", "password": "Carlos" } | * It should show status 401 Unauthorized | * 401 Unauthorized was obtained |  |  | PASSED
TC8: Validate Unable to log in leaving Username empty and Password incorrect. |  | TC9: Validate failure to log in by using the incorrect username and password null. | { "username": null, "password": "Carlos" } | * It should show status 400 Bad Request | * 400 Bad Requests were received |  |  | PASSED
TC9: Validate Unable to log in using Incorrect Username and Empty Password. |  | TC9: Validate failure to log in by using the incorrect username and password null. | { "username": "Reinaldo", "password": null } | * It should show status 400 Bad Request | * 400 Bad Requests were received |  |  | PASSED
TC10: Validate successful session close | [5 empty] | This TC will not run because this functionality is not available.
Create Product
Description | Preconditions | Action | Data | Expected Results | Results Obtained | Observaciones | Evidence | PASS | Bugs | Bugs
TC11: Validate that you can successfully create a product | *The user must be logged in | * Create the product using the POST method with the URL {{base_url}}/api/Product | { "id": 1, "name": "Galletas", "price": 2 } | * It should show status 200 OK. | *A 201 Craete was obtained | The product is created but it should give 200 OK as indicated in the documentation. |  | NOT PASSED | Bug 1
TC12: Validate not being able to create a Product using invalid id |  | * Create the product using the POST method with the URL {{base_url}}/api/Product | { "id": "No", "name": "Galletas", "price": 232 } | * It should show status 400 Bad Request | * 400 Bad Requests were received |  |  | PASSED
TC13: Validate not being able to create a Product using an invalid name |  | * Create the product using the POST method with the URL {{base_url}}/api/Product | { "id": 2, "name": 123456, "price": 232 } | * It should show status 400 Bad Request | * 400 Bad Requests were received |  |  | PASSED
TC14: Validate not being able to create a Product using an invalid price |  | * Create the product using the POST method with the URL {{base_url}}/api/Product | { "id": 2, "name": "Arroz", "price": "Josefina" } | * It should show status 400 Bad Request | * 400 Bad Requests were received |  |  | PASSED
TC15: Validate that a Product cannot be created using a negative price |  | * Create the product using the POST method with the URL {{base_url}}/api/Product | { "id": 2, "name": "Arroz", "price": -1234 } | * It should show status 400 Bad Request | * 201 Create were received *Create product with negative price | Create product with negative price |  | NOT PASSED | Bug 2
TC16: Validate not being able to create a Product using all invalid data |  | * Create the product using the POST method with the URL {{base_url}}/api/Product | { "id": -12, "name": 8.8, "price": # } | * It should show status 400 Bad Request | * 400 Bad Requests were received | I propose improving the way the server handles error responses, particularly in cases where more than one error is detected in the submitted data. Currently, it seems that the server only returns a message indicating a single error, which can make it difficult for the user to identify and resolve all issues at once. |  | PASSED
TC17: Validate not being able to create a Product leaving the id field Null |  | * Create the product using the POST method with the URL {{base_url}}/api/Product | { "id": null, "name": "caramelos", "price": 8 } | * It should show status 400 Bad Request | * 400 Bad Requests were received |  |  | PASSED
TC18: Validate not being able to create a Product leaving the name field Null |  | * Create the product using the POST method with the URL {{base_url}}/api/Product | { "id": 8, "name": null, "price": 3 } | * It should show status 400 Bad Request | *A 201 Craete was obtained *Create the product with the name null | Create the product with the name null |  | NOT PASSED | Bug 3
TC19: Validate not being able to create a Product leaving the price field Null |  | * Create the product using the POST method with the URL {{base_url}}/api/Product | { "id": 5, "name": "Chocolate", "price": null } | * It should show status 400 Bad Request | * 400 Bad Requests were received |  |  | PASSED
TC20: Validate not being able to create a Product leaving all fields Null |  | * Create the product using the POST method with the URL {{base_url}}/api/Product | { "id": 6, "name": "Chocolate", "price": null } | * It should show status 400 Bad Request | * 400 Bad Requests were received |  |  | PASSED
TC21: Validate not being able to create a Product using a previously used id |  | * Create the product using the POST method with the URL {{base_url}}/api/Product | { "id": "{{idproduct}}", "name": "Chocolate", "price": 23 } | * It should show status 400 Bad Request | *A 201 Craete was obtained *Create the product with the name null | Create product with id already used which can cause a big problem in the system |  | NOT PASSED | Bug 4
Get Product
Description | Preconditions | Action | Data | Expected Results | Results Obtained | Observaciones | Evidence | PASS | Bugs
TC22: Validate that can successfully obtain all the products from the list | *The user must have previously created the products | * Get the product using the Get method with the URL {{base_url}}/api/Product/ | N/A | * It should show status 200 OK. | * Status 200 was obtained. |  |  | PASSED
TC23: Validate the ability to obtain a specific Product by ID |  | * Get the product using the Get method with the URL {{base_url}}/api/Product/{{idproduct}} | N/A | * It should show status 200 OK. | * Status 200 was obtained. |  |  | PASSED
TC24: Validate unable to get Product using incorrect id |  | * Get the product using the Get method with the URL {{base_url}}/api/Product/{{idIncorrecto}} | N/A | * It should show status 404 Not Found | *The status 404 Not Found was obtained |  |  | PASSED
TC25: Validate not being able to obtain Product leaving id Null |  | * Get the product using the Get method with the URL {{base_url}}/api/Product/null | N/A | * It should show status 400 Bad Request | * 400 Bad Requests were received |  |  | PASSED
Put Product
Description | Preconditions | Action | Data | Expected Results | Results Obtained | Observaciones | Evidence | PASS | Bugs | Bugs
TC26: Validate that can successfully update your product | *The user must have previously created products | * Update the product using the Put method with the URL {{base_url}}/api/Product/{{idproduct}} | { "id": 10, "name": "Galletas 23", "price": 7 } | *Should display a 200 OK status *Should update all fields | *Displays a 204 No Content status * Do not update the ID | *It doesn't respond with the status it should and doesn't update the ID. *The status bug has already been reported in the product creation, so I'll only reference that bug, and the bug regarding the ID update will be raised, which is very important. |  | NOT passed | Bug 1 | Bug 5
TC27: Validate not being able to update Product using a non-existent product id |  | * Update the product using the Put method with the URL {{base_url}}/api/Product/{{idIncorrecto}} | { "id": 10, "name": "Galletas 23", "price": 3 } | * It should show status 404 Not Found | *The status 404 Not Found was obtained |  |  | PASSED
TC28: Validate cannot update Product when id is Null |  | * Update the product using the Put method with the URL {{base_url}}/api/Product/ | { "id": 10, "name": "Galletas 23", "price": 3 } | *Should show a 405 status Method Not Allowed | *Displays a status 405 Method Not Allowed |  |  | PASSED
TC29: Validate unable to update Product using invalid id |  | * Update the product using the Put method with the URL {{base_url}}/api/Product/{{idproduct}} | { "id": "carla", "name": "Galletas 23", "price": 3 } | * It should show status 400 Bad Request | * 400 Bad Requests were received |  |  | PASSED
TC30: Validate unable to update Product using invalid name |  | * Update the product using the Put method with the URL {{base_url}}/api/Product/{{idproduct}} | { "id": 897, "name": 23867, "price": 3 } | * It should show status 400 Bad Request | * 400 Bad Requests were received |  |  | Passed
TC31: Validate not being able to update Product when price has negative values |  | * Update the product using the Put method with the URL {{base_url}}/api/Product/{{idproduct}} | { "id": 23, "name": "chupeta", "price": -3 } | * It should show status 400 Bad Request | *Shows a status of 204 No Content *Updates product with negative price | *The negative price creation bus has already been lifted, in this case I will refer to that bug |  | NOT PASSED | Bug 2
TC32: Validate not being able to update Product by entering all incorrect values |  | * Update the product using the Put method with the URL {{base_url}}/api/Product/{{idproduct}} | { "id": "hola", "name": 2345, "price": "jose" } | * It should show status 400 Bad Request | * 400 Bad Requests were received |  |  | PASSED
TC33: Validate not being able to update Product when leaving id null |  | * Update the product using the Put method with the URL {{base_url}}/api/Product/{{idproduct}} | { "id": null, "name": "mayonesa", "price": 45 } "id": "hola", "name": 2345, "price": "jose" } | * It should show status 400 Bad Request | * 400 Bad Requests were received |  |  | PASSED
TC34: Validate not being able to update Product when name is null |  | * Update the product using the Put method with the URL {{base_url}}/api/Product/{{idproduct}} | { "id": 2345, "name": null, "price": 45 } | * It should show status 400 Bad Request | *Shows a status of 204 No Content. *Updates product names with name null | *The name null bug has been raised previously so I will refer to that bug. |  | NOT PASSED | Bug 3
TC35: Validate not being able to update Product when price is null |  | * Update the product using the Put method with the URL {{base_url}}/api/Product/{{idproduct}} | { "id": 2345, "name": "aguacate", "price": null } | * It should show status 400 Bad Request | * 400 Bad Requests were received |  |  | PASSED
TC36: Validate not being able to update Product leaving all Null values. |  | * Update the product using the Put method with the URL {{base_url}}/api/Product/{{idproduct}} | { "id": null, "name": null, "price": null } | * It should show status 400 Bad Request | * 400 Bad Requests were received |  |  | PASSED
TC37: Validate not being able to update Product because it has 2 duplicate IDs |  | * Update the product using the Put method with the URL {{base_url}}/api/Product/{{idproduct}} | { "id": 1, "name": "MAria", "price": 34 } | * It should show status 400 Bad Request | *Shows a status of 204 No Content *Updates product IDs that have already been used | *The bug of using duplicate ids has already been reported, so I will refer to that bug. |  | NOT PASSED | Bug 4
Description | Preconditions | Action | Data | Expected Results | Results Obtained | Observaciones | Evidence | PASS | Bugs
TC38: Validate ability to delete Product | *The product with the id used must be added | * Delete the product using the DELETE method with the URL {{base_url}}/api/Product/{{idproduct}} | N/A | * It should show status 200 OK. | *Shows a status of 204 No Content |  |  | NOT PASSED | Bug 1
TC39: Validate not being able to delete Product when the id is invalid |  | * Delete the product using the DELETE method with the URL {{base_url}}/api/Product/{{idiInvalido}} | N/A | * It should show status 400 Bad Request | * 400 Bad Requests were received |  |  | PASSED
TC40: Validate that the Product cannot be deleted when the ID is left Null. |  | * Delete the product using the DELETE method with the URL {{base_url}}/api/Product/ | N/A | *Should show a 405 status Method Not Allowed | *Displays a status 405 Method Not Allowed |  |  | PASSED
TC41: Validate not being able to delete Product when using a non-existent id |  | * Delete the product using the DELETE method with the URL {{base_url}}/api/Product/{{idIncorrecto}} | N/A | * It should show status 404 Not Found | *The status 404 Not Found was obtained |  |  | PASSED
Create Order
Description | Preconditions | Action | Data | Expected Results | Results Obtained | Observaciones | Evidence | PASS | Bugs
TC42: Validate successful order creation | *The user must be logged in | * Create order using POST method with URL {{base_url}}/api/order | { "id": 1, "productName": "Harina", "quantity": 10, "status": "Activo" } | * It should show status 200 OK. | *A 201 Craete was obtained | *Sends status 201 Created when it should be 200 Ok |  | NOT PASSED | Bug 6
TC43: Validate unable to create order using an invalid id |  | * Create order using POST method with URL {{base_url}}/api/order | { "id": "maria", "productName": "Harina", "quantity": 10, "status": "Activo" } | * It should show status 400 Bad Request | * 400 Bad Requests were received |  |  | PASSED
TC44: Validate unable to create order using invalid product Name |  | * Create order using POST method with URL {{base_url}}/api/order | { "id": 1, "productName": 23489, "quantity": 10, "status": "Activo" } | * It should show status 400 Bad Request | * 400 Bad Requests were received |  |  | PASSED
TC45: Validate not being able to create order using an invalid quantity |  | * Create order using POST method with URL {{base_url}}/api/order | { "id": 1, "productName": "Ludywheb 23", "quantity": "jsaodhgu", "status": "Activo" } | * It should show status 400 Bad Request | * 400 Bad Requests were received |  |  | PASSED
TC46: Validate unable to create order using an invalid status |  | * Create order using POST method with URL {{base_url}}/api/order | { "id": 1, "productName": "Ludywheb 23", "quantity": 23456, "status": 423456 } | * It should show status 400 Bad Request | * 400 Bad Requests were received |  |  | PASSED
TC47: Validate unable to create order using all invalid values |  | * Create order using POST method with URL {{base_url}}/api/order | { "id": !/()#, "productName": 23763, "quantity": "letras", "status": 423456 } | * It should show status 400 Bad Request | * 400 Bad Requests were received | I propose improving the way the server handles error responses, particularly in cases where more than one error is detected in the submitted data. Currently, it seems that the server only returns a message indicating a single error, which can make it difficult for the user to identify and resolve all issues at once. |  | PASSED
TC48: Validate not being able to create order when the id is Null |  | * Create order using POST method with URL {{base_url}}/api/order | { "id": null, "productName": "Corazon", "quantity": 23, "status": "activo" } | * It should show status 400 Bad Request | * 400 Bad Requests were received |  |  | PASSED
TC49: Validate the ability to create order by leaving the Product Name field Null |  | * Create order using POST method with URL {{base_url}}/api/order | { "id": 323, "productName": null, "quantity": 23, "status": "activo" } | * It should show status 400 Bad Request | *A 201 Craete was obtained | Allows you to create an order with a null productName |  | NOT PASSED | Bug 7
TC50: Validate not being able to create order leaving the quantity field Null |  | * Create order using POST method with URL {{base_url}}/api/order | { "id": 323, "productName": "carne", "quantity": null, "status": "activo" } | * It should show status 400 Bad Request | * 400 Bad Requests were received |  |  | PASSED
TC51: Validate the ability to create order by leaving the status Null |  | * Create order using POST method with URL {{base_url}}/api/order | { "id": 323, "productName": "carne", "quantity": 98, "status": null } | * It should show status 400 Bad Request | *A 201 Craete was obtained | *An order is created that has a null status |  | NOT PASSED | Bug 8
TC52: Validate not being able to create order, leaving all fields null |  | * Create order using POST method with URL {{base_url}}/api/order | { "id": null, "productName": null, "quantity": null, "status": null } | * It should show status 400 Bad Request | * 400 Bad Requests were received |  |  | PASSED
TC53: Validate not being able to create order with equal IDs |  | * Create order using POST method with URL {{base_url}}/api/order | { "id": 1, "productName": "Huesos", "quantity": 13, "status": "Activo" } | * It should show status 400 Bad Request | * 400 Bad Requests were received | *Allows you to create orders with IDs that are already being used |  | NOT PASSED | Bug 9
Get Order
Description | Preconditions | Action | Data | Expected Results | Results Obtained | Observaciones | Evidence | PASS | Bugs
TC54: Validate that can successfully obtain all orders | *The user must have created an order | * Get order using GET method with URL {{base_url}}/api/order | N/A | * It should show status 200 OK. | * Status 200 was obtained. |  |  | PASSED
TC55: Validate that you can successfully obtain the requested order |  | * Get order using GET method with URL {{base_url}}/api/order/{{idorder}} | N/A | * It should show status 200 OK. | * Status 200 was obtained. |  |  | PASSED
TC56: Validate not being able to obtain order by entering a non-existent ID |  | * Get order using GET method with URL {{base_url}}/api/order/{{idOrderInexistente}} | N/A | * It should show status 404 Not Found | *The status 404 Not Found was obtained |  |  | PASSED
TC57: Validate unable to obtain order by leaving the id Null |  | * Get order using GET method with URL {{base_url}}/api/order/null | N/A | * It should show status 400 Bad Request | * 400 Bad Requests were received |  |  | PASSED
Put order
Description | Preconditions | Action | Data | Expected Results | Results Obtained | Observaciones | Evidence | PASS | Bugs | Bugs
TC58: Validate update of an order successfully | *The user must save the order beforehand | * Update the order using the PUT method with the URL {{base_url}}/api/order/{{idorder}} | { "id": 2, "productName": "Maiz", "quantity": 98, "status": "activo" } | * It should show status 200 OK. | *Shows a status of 204 No Content | Does not update the order id |  | NOT PASSED | Bug 6 | Bug 10
TC59: Validate unable to update order using invalid id |  | * Update the order using the PUT method with the URL {{base_url}}/api/order/{{idorderinva}} | { "id": 2, "productName": "Maiz", "quantity": 98, "status": "activo" } | * It should show status 404 Not Found | *The status 404 Not Found was obtained |  |  | PASSED
TC60: Validate unable to update order using Null id |  | * Update the order using the PUT method with the URL {{base_url}}/api/order/null | { "id": 2, "productName": "Maiz", "quantity": 98, "status": "activo" } | * It should show status 400 Bad Request | * 400 Bad Requests were received |  |  | PASSED
TC61: Validate not being able to update order using invalid id |  | * Update the order using the PUT method with the URL {{base_url}}/api/order/{{idorder}} | { "id": "jos", "productName": "Maiz", "quantity": 98, "status": "activo" } | * It should show status 400 Bad Request | * 400 Bad Requests were received |  |  | PASSED
TC62: Validate unable to update order using invalid product name |  | * Update the order using the PUT method with the URL {{base_url}}/api/order/{{idorder}} | { "id": 4, "productName": 3.4, "quantity": 98, "status": "activo" } | * It should show status 400 Bad Request | * 400 Bad Requests were received |  |  | PASSED
TC63: Validate unable to update order using invalid quantity |  | * Update the order using the PUT method with the URL {{base_url}}/api/order/{{idorder}} | { "id": 4, "productName": "Miwuseyh", "quantity": "skfh", "status": "activo" } | * It should show status 400 Bad Request | * 400 Bad Requests were received |  |  | PASSED
TC64: Validate unable to update order using invalid status |  | * Update the order using the PUT method with the URL {{base_url}}/api/order/{{idorder}} | { "id": 4, "productName": "Miwuseyh", "quantity": 134, "status": #%/ } | * It should show status 400 Bad Request | * 400 Bad Requests were received |  |  | PASSED
TC65: Validate unable to update order using all invalid values |  | * Update the order using the PUT method with the URL {{base_url}}/api/order/{{idorder}} | { "id": "jh", "productName": 2, "quantity": "koij", "status": 23 } | * It should show status 400 Bad Request | * 400 Bad Requests were received | I propose improving the way the server handles error responses, particularly in cases where more than one error is detected in the submitted data. Currently, it seems that the server only returns a message indicating a single error, which can make it difficult for the user to identify and resolve all issues at once. |  | PASSED
TC66: Validate cannot update order because the id field is null |  | * Update the order using the PUT method with the URL {{base_url}}/api/order/{{idorder}} | { "id": null, "productName": "khj", "quantity": 233, "status": "activo" } | * It should show status 400 Bad Request | * 400 Bad Requests were received |  |  | PASSED
TC67: Validate unable to update order using null product name field |  | * Update the order using the PUT method with the URL {{base_url}}/api/order/{{idorder}} | { "id": 9, "productName": null, "quantity": 98, "status": "activo" } | * It should show status 400 Bad Request | *Shows a status of 204 No Content |  |  | NOT PASSED | Bug 10
TC68: Validate cannot update order because the quantity field is null |  | * Update the order using the PUT method with the URL {{base_url}}/api/order/{{idorder}} | { "id": 9, "productName": "Chevere", "quantity": null, "status": "activo" } | * It should show status 400 Bad Request | * 400 Bad Requests were received |  |  | PASSED
TC69: Validate cannot update order with null status |  | * Update the order using the PUT method with the URL {{base_url}}/api/order/{{idorder}} | { "id": 9, "productName": "Chevere", "quantity": 78, "status": null } | * It should show status 400 Bad Request | *Shows a status of 204 No Content |  |  | NOT PASSED | Bug 10
TC70: Validate cannot update order by leaving all fields null |  | * Update the order using the PUT method with the URL {{base_url}}/api/order/{{idorder}} | { "id": null, "productName": null, "quantity": null, "status": null } | * It should show status 400 Bad Request | * 400 Bad Requests were received | I propose improving the way the server handles error responses, particularly in cases where more than one error is detected in the submitted data. Currently, it seems that the server only returns a message indicating a single error, which can make it difficult for the user to identify and resolve all issues at once. |  | PASSED
TC71: Validate not being able to update an ID when it has already been used previously |  | * Update the order using the PUT method with the URL {{base_url}}/api/order/{{idorder}} | { "id": 1, "productName": "kajdj", "quantity": 23, "status": "active" } | * It should show status 400 Bad Request | *Shows a status of 204 No Content |  |  | NOT PASSED | Bug 10
Delect order
Description | Preconditions | Action | Data | Expected Results | Results Obtained | Observaciones | Evidence | PASS | Bugs
TC72: Validate successful delete of order | *The user must have previously saved the order | * Delete the order using the DELETE method with the URL {{base_url}}/api/order/{{idorder}} | N/A | * It should show status 200 OK. | *Shows a status of 204 No Content | *Delete but send status 204 |  | NOT PASSED | Bug 6
TC73: Validate cannot delete order with non-existent ID |  | * Delete the order using the DELETE method with the URL {{base_url}}/api/order/{{idOrderInexistente}} | N/A | * It should show status 404 Not Found | *The status 404 Not Found was obtained |  |  | PASSED
TC74: Validate unable to delete order with invalid id |  | * Delete the order using the DELETE method with the URL {{base_url}}/api/order/{{idOrderString}} | N/A | * It should show status 400 Bad Request | * 400 Bad Requests were received |  |  | PASSED
TC75: Validate cannot delete order with Null id |  | * Delete the order using the DELETE method with the URL {{base_url}}/api/order/null | N/A | * It should show status 400 Bad Request | * 400 Bad Requests were received |  |  | PASSED

## BUGS BACKEND
Bugs Backend
Affected test cases | Bug names | Steps to reproduce bugs | Expected Result (Output) | Actual Result (Behavior) | Priority | Evidence
TC11 TC26 TC38 | Bug 1 ¦ Product ¦ HTTP Status Code Error: 201 Created Returned Instead of 200 OK | Perform the following steps in Postman: Select the collection: QA Challenge Click on the folder: Product Management Click on the folder: Create Product Click on the folder: TC11: Validate successful creation of a product Select the request: Create product and send the request with the following: POST: {{base_url}}/api/Product Body: { "id": 1, "name": "Galletas", "price": 2 } With the following script: const body = pm.response.json(); pm.collectionVariables.set("idproduct", body.id) pm.test("It should show a status 200 ok", ()=>{ pm.response.to.have.status(200) }) Click on send the request: The server returns the response with a status of 201 Create, creating the product. | *Should give status 200 ok | *Returns a 201 created status | Moderate
TC15 TC31 | Bug 2 ¦ Product ¦ Allows you to create a product with a negative price | Perform the following steps in Postman: Select the collection: QA Challenge Click on the folder: Product Management Click on the folder: Create Product Click on the folder: TC15: Validate failure to create a product using a negative price Select the request: Do not create product and send the request with the following: POST: {{base_url}}/api/Product Body: { "id": 2, "name": "Arroz", "price": -1234 } With the following script: const body = pm.response.json(); pm.test("It should show a status 400 Bad Request", ()=>{ pm.response.to.have.status(400) }); Click on send the request: The server returns the response with a status of 201 Create, thus showing that the product with a negative price was created. | Should return a Status of 400 Bad Request. | *A 201 Craete was obtained *Create the product with the negative price | Very high
TC18 TC34 | Bug 3 ¦ Producto ¦ Allows you to create a product without a name (Null) | Perform the following steps in Postman: Select the collection: QA Challenge Click on the folder: Product Management Click on the folder: Create Product Click on the folder: TC18: Validate failure to create a product with the name field null Select the request: Do not create product and send the request with the following: POST: {{base_url}}/api/Product Body: { "id": 8, "name": null, "price": 3 } With the following script: const body = pm.response.json(); pm.collectionVariables.set("idproductNameNUll", body.id) pm.test("It should show a status 400 Bad Request", ()=>{ pm.response.to.have.status(400) }) Click on send the request: The server returns the response with a status of 201 Create, thus showing that the product with name null was created. | Should return a Status of 400 Bad Request. | *Returns a 201 created *A product with name null is created | High
TC21 TC37 | Bug 4 ¦ Producto ¦ Create product with previously used Ids | "Perform the following steps in Postman: Select the collection: QA Challenge Click on the folder: Product Management Click on the folder: Create Product Click on the folder: TC21: Validate not being able to create a Product using a previously used id Select the request: Do not create product and send the request with the following: POST: {{base_url}}/api/Product Body: { "id": "{{idproduct}}", "name": "Chocolate", "price": 23 } With the following script: const body = pm.response.json(); pm.test("It should show a status 400 Bad Request", ()=>{ pm.response.to.have.status(400) }) Click on send the request | Should return a Status of 400 Bad Request. | *Returns a 201 created status *A product is created with a previously used id | Very high
TC26 | Bug 5 ¦ Producto ¦ Does not update product id | Perform the following steps in Postman: Select the collection: QA Challenge Click on the folder: Product Management Click on the folder: Put Product Click on the folder: TC21: Validate not being able to create a Product using a previously used id Select the request: Put product and send the request with the following: PUT: {{base_url}}/api/Product/{{idproduct}} Body: { "id": 10, "name": "Galletas 23", "price": 7 } With the following script: const body = pm.response.text(); pm.collectionVariables.set("idProductActualizado", body.id) pm.test("It should show a status 200 ok", ()=>{ pm.response.to.have.status(200); }); Select the request: Get product and send the request with the following: GET: {{base_url}}/api/Product/{{idproduct}} With the following script: const body = pm.response.json(); const expectedId= 10; const expectedName= "Galletas23"; const expectedPrice= 7; pm.test("It should show a status 200 Created", ()=>{ pm.response.to.have.status(200); }); pm.test("It should show expeted Results", ()=>{ pm.expect(body.id).to.eql(expectedId); pm.expect(body.name).to.eql(expectedName); pm.expect(body.price).to.eql(expectedPrice); });Click on send the request: In the execution of the get request we can see that the other fields are updated but the id is not. | *Should display a 200 OK status *Should update all fields | *Displays a 204 No Content status * Do not update the ID | Very High
TC 42 TC72 | Bug 6 ¦ Order ¦ Incorrect HTTP Status Code on Order Creation (201 Created instead of 200 OK) | Perform the following steps in Postman: Select the collection: QA Challenge Click on the folder: Order Processing Click on the folder: Create Order Click on the folder: TC42: Validate order creation successfully Select the request: Create order and send the request with the following: POST:{{base_url}}/api/order Body: { "id": 1, "productName": "Harina", "quantity": 10, "status": "Activo" } With the following script: const body = pm.response.json(); pm.collectionVariables.set("idorder", body.id) pm.test("It should show a status 200 Ok", ()=>{ pm.response.to.have.status(200); }); Click on send the request Select the request: Get order and send the request with the following: GET:{{base_url}}/api/order/{{idorder}} With the following script: const body = pm.response.json(); pm.test("It should show a status 200 ok", ()=>{ pm.response.to.have.status(200); }); Click on send the request | *Should give status 200 ok | *Returns a 201 created status | Moderate
TC49 | Bug 7¦ Order ¦ Allows you to create an order with a null Productname | Perform the following steps in Postman: Select the collection: QA Challenge Click on the folder: Order Processing Click on the folder: Create Order Click on the folder: TC49: Validate order creation failure leaving productName field null Select the request: Not creating order and send the request with the following: POST:{{base_url}}/api/order Body: { "id": 323, "productName": null, "quantity": 23, "status": "activo" } With the following script: const body = pm.response.json(); pm.test("It should show a status 400 Bad Request", ()=>{ pm.response.to.have.status(400); });Click on send the request | * It should show status 400 Bad Request | *A 201 Craete was obtained *An order is created with ProductName null | High
TC51 | Bug 8 ¦ Order ¦ Bug in the restriction mechanism: 'status' allows null values ​​to be assigned | Perform the following steps in Postman: Select the collection: QA Challenge Click on the folder: Order Processing Click on the folder: Create Order Click on the folder: TC51: Validate order creation failure leaving status null Select the request: Not creating order and send the request with the following: POST:{{base_url}}/api/order Body: { "id": 323, "productName": "carne", "quantity": 98, "status": null } With the following script: const body = pm.response.json(); pm.test("It should show a status 400 Bad Request", ()=>{ pm.response.to.have.status(400); }); Click on send the request | * It should show status 400 Bad Request | *A 201 Craete was obtained. *An order is created that has a null status | High
TC53 | Bug 9 ¦ Order ¦*Validation failed: creation of orders with existing identifiers is allowed | Perform the following steps in Postman: Select the collection: QA Challenge Click on the folder: Order Processing Click on the folder: Create Order Click on the folder:TC53: Validate order creation failure with identical ids Select the request: Not creating order and send the request with the following: POST:{{base_url}}/api/order Body: { "id": 1, "productName": "Huesos", "quantity": 13, "status": "Activo" } With the following script: const body = pm.response.json(); pm.test("It should show a status 400 Bad Request", ()=>{ pm.response.to.have.status(400); }); Click on send the request | * It should show status 400 Bad Request | *Returns a 201 created status *Creates order with existing ID | Very high
TC58 TC69 TC67 | Bug 10 ¦ Order ¦ Does not update the order | Perform the following steps in Postman: Select the collection: QA Challenge Click on the folder: Product Management Click on the folder: Put Product Click on the folder: TC58: Validate update of an order successfully Select the request: Put product and send the request with the following: PUT: {{base_url}}/api/order/{{idorder}} Body: { "id": 2, "productName": "Maiz", "quantity": 98, "status": "activo" } const body = pm.response.text(); pm.test("It should show a status 200 ok", ()=>{ pm.response.to.have.status(200); }); Select the request: Get order and send the request with the following: GET:{{base_url}}/api/order/{{idorder}} With the following script: const body = pm.response.json(); const expectedID= 2; const expectedproductName= "Maiz"; const expectedquantity= 98; const expectedstatus= "activo"; pm.collectionVariables.set("idOrderActualizado", body.id) pm.test("It should show a status 200 Created", ()=>{ pm.response.to.have.status(200); }); pm.test("It should show expeted Results", ()=>{ pm.expect(body.id).to.eql(expectedID); pm.expect(body.productName).to.eql(expectedproductName); pm.expect(body.quantity).to.eql(expectedquantity); pm.expect(body.status).to.eql(expectedstatus); });Click on send the request | *Should display a 200 OK status *Should update all fields" | *Displays a 204 No Content status * Does not update | Very high

## FRONTED TEST EXECUTE
Frontend Test Execute and Reporting
Description | Preconditions | Action | Data | Expected Results | Results Obtained | Observaciones | Evidence | PASS | Bug
TC1: Validate successful login by entering the correct username and password. | *The user must be previously registered. *The user must be logged in to the user authentication interface. *The user must have a username and password. | *Enter valid username and password | username: testuser password: password | *The user must log in | *Login successfully | *When logging in, the token may be displayed, which can cause security issues. |  | PASSED
TC2: Validate that cannot log in by leaving the Username field empty and the Password correct. |  | *Leave the username field empty and the password field valid | username: password: password | *It should login failed | *Login failed |  |  | PASSED
TC3: Validate Unable to log in using correct Username and empty Password. |  | Enter a valid username and leave the password field empty. | username: testuser password: | *It should login failed | *Login failed |  |  | PASSED
TC4: Validate Unable to log in leaving all fields empty. |  | Send both the username and password fields empty. | username: password: | *It should login failed | *Login failed |  |  | PASSED
TC5: Validate Unable to log in using correct Username and incorrect Password. |  | Enter the correct username and an invalid password. | username: testeruser password: !##%/&()(&%&#" | *It should login failed | *Login failed |  |  | PASSED
TC6: Validate Unable to log in using incorrect username and correct password. |  | Enter invalid data in both fields | username: 23345 password: "vgersder" | *It should login failed | *Login failed |  |  | PASSED
TC7: Validate Unable to log in leaving Username empty and Password incorrect. |  | Send the username field empty and the password field invalid | username: password: 12345678 | *It should login failed | *Login failed |  |  | PASSED
TC8: Validate Unable to log in using Incorrect Username and Empty Password. |  | Send the name field invalid and the password field empty. | username: juan password: 12345678 | *It should login failed | *Login failed |  |  | PASSED
TC9: Validate successful session close
Improvement Proposal: To optimize user experience, it is recommended to implement clear and specific error messages that indicate exactly which field is invalid or requires correction. This will allow users to identify and resolve the issue efficiently, improving the system's perceived quality and avoiding confusion. An example could be: 'The username field cannot be empty.' 'The entered username is invalid. Please verify and try again.' With this improvement, the interaction becomes more intuitive and aligns with best practices in interface design and usability.